## Risk Assessment Matrix
x
SCALE OF SEVERITY
SCALE OF LIKELIHOOD |  | ACCEPTABLE | TOLERABLE | GENERALLY UNACCEPTABLE
| NOT LIKELY | LOW | MEDIUM | MEDIUM
| POSSIBLE | LOW | MEDIUM | HIGH
| PROBABLE | MEDIUM | HIGH | HIGH

## CategoryLists
SEVERITY | LIKELIHOOD | IMPACT
Acceptable | Not likely | Low
Tolerable | Possible | Medium
Generally unacceptable | Probable | High

## 2019_RA (hidden)
Hula Risk Assessment List (Q1/Q2 2019)
RISK | AREAS AFFECTED | SEVERITY | LIKELIHOOD | RISK IMPACT | RECOMMENDED ACTION(S)
Inadequate cash flow | Finance & Accounting | Generally unacceptable | Not likely | Medium | Board of directors quarterly financial review Maintenance of stated cash reserves Review Line of Credit relative to cash flow demands
Aggressive growth leading to non-compliance or process breached | Human Resources | Generally unacceptable | Possible | High | CEO monitors compliance against all new hire processes Expand job scope for HR/Benefits Consultant to include process compliance
Offshore Development Team Eliminated or Key Resource Turnover | Product Development | Generally unacceptable | Not likely | Medium | Comprehensive annual vendor review Automated Source Code Management Solution Development Documentation in line with ITIL Standards Eliminate single threading on offshore team Establish Project Manager Role within Offshore Dev Team
MSFT Azure Data Center Outage | Product Availability | Generally unacceptable | Possible | High | Redundency plan inclusive of geogrpahical replication and communicated RPO/RTO Review of Azure SLAs and General Industry Reviews Annual tabletop exercise to test restore plan
Growth of European Customer Base puts us out of compliance with GDPR | Data Privacy | Generally unacceptable | Possible | High | Establish EU Data Center option Maintain Privacy Shield certification Update Privacy and Security policies as required
Lack of SOC2 Certification could cause customer attrition due to size and complexity of customer base | Customer Success | Generally unacceptable | Probable | High | Execute on SOC2 audit in 2019

## 2020_RA (hidden)
Kahuna Risk Assessment List (Q1/Q2 2020)
RISK | AREAS AFFECTED | SEVERITY | LIKELIHOOD | RISK IMPACT | CHANGE FROM LAST RISK ASSESSMENT | RECOMMENDED ACTION(S)
Inadequate cash flow | Finance & Accounting | Generally unacceptable | Possible | Medium | Y-COVID situation has increased likelihood due to market conditions. Additional mitigations necessary. | Board of directors quarterly financial review Maintenance of stated cash reserves Review Line of Credit relative to cash flow demands SBA Loan Programs, secured (PPP and EIDL). Company performed well in terms of securing credit facilities even in the face of difficult processes and limited funding available. Proactive financial modeling to account for various financial scenarios and monitoring of current customer commitment follow through to enact these scenarios.
Aggressive growth leading to non-compliance or process breached | Human Resources | Tolerable | Not likely | Low | Y-Company has grown through aggrssive growth and maintained processes. Documentation and training of process has been formalized. | CEO monitors compliance against all new hire processes Expand job scope for HR/Benefits Consultant to include process compliance - COMPLETED in 2019 Documented processes
Offshore Development Team Eliminated or Key Resource Turnover | Product Development | Generally unacceptable | Not likely | Medium | N | Comprehensive annual vendor review Automated Source Code Management Solution Development Documentation in line with ITIL Standards Eliminate single threading on offshore team Establish Project Manager Role within Offshore Dev Team
MSFT Azure Data Center Outage | Product Availability | Generally unacceptable | Possible | High | N | Redundency plan inclusive of geogrpahical replication and communicated RPO/RTO Review of Azure SLAs and General Industry Reviews Annual tabletop exercise to test restore plan
Growth of European Customer Base puts us out of compliance with GDPR | Data Privacy | Generally unacceptable | Not likely | Medium | Y-SOC2 Compliance with GDPR EU DataCenter Option formalized | Establish EU Data Center option-COMPLETE Maintain Privacy Shield certification Update Privacy and Security policies as required
Lack of SOC2 Certification could cause customer attrition due to size and complexity of customer base | Customer Success | Generally unacceptable | Not likely | Medium | Y-SOC2 Certification Completed | Execute on SOC2 audit in 2020-COMPLETED in 2019 and Renewed in 2020.
COVID-19 work environment causes security and or other process issues. Further COVID may present issues or delays in projects. | Operations | Generally unacceptable | Possible | High | Y-New Risk Identified | Condudted a full process lifecycle risk identification and determined low risk. Establish scalable processes and support mechanisms (Remote work, Infrastructure) Provided formal customer and employee communications at various stages in response.
External Market Conditions (Oil Prices) cause Churn in Customer Base | Sales | Tolerable | Probable | Medium | Y-New Risk Identified | Expansion/Diversification into other verticals (i.e. Healthcare, Manufacturing, Aerospace) 2020 performance has included expansion at Lockheed and 2019/2020 new customer verticals such as Healthcare, Professional Services, Technology and Manufacturing

## 2021_RA (hidden)
Kahuna Risk Assessment List (Q1/Q2 2021)
RISK | AREAS AFFECTED | SEVERITY | LIKELIHOOD | RISK IMPACT | CHANGE FROM LAST RISK ASSESSMENT | RECOMMENDED ACTION(S)
Inadequate cash flow | Finance & Accounting | Generally unacceptable | Not likely | Medium | Y-COVID situation has increased likelihood due to market conditions. Additional mitigations necessary. | Board of directors quarterly financial review Maintenance of stated cash reserves Review Line of Credit relative to cash flow demands SBA Loan Programs, secured (PPP and EIDL). Company performed well in terms of securing credit facilities even in the face of difficult processes and limited funding available. Proactive financial modeling to account for various financial scenarios and monitoring of current customer commitment follow through to enact these scenarios.
Aggressive growth leading to non-compliance or process breached | Human Resources | Tolerable | Not likely | Low | Y-Company has grown through aggrssive growth and maintained processes. Documentation and training of process has been formalized. | CEO monitors compliance against all new hire processes Expand job scope for HR/Benefits Consultant to include process compliance - COMPLETED in 2019 Documented processes
Offshore Development Team Eliminated or Key Resource Turnover | Product Development | Generally unacceptable | Not likely | Low | Y- Removed large portion of dependency on key resources by bringing development resources in house. Have taken ownership of IP from development side. | Comprehensive annual vendor review Automated Source Code Management Solution Development Documentation in line with ITIL Standards Eliminate single threading on offshore team Establish Project Manager Role within Offshore Dev Team
MSFT Azure Data Center Outage | Product Availability | Generally unacceptable | Possible | High | Y- Reduced Risk after application of mitigation actions specific to tabletop exercise. | Redundency plan inclusive of geographical replication and communicated RPO/RTO Review of Azure SLAs and General Industry Reviews Annual tabletop exercise to test restore plan
COVID-19 work environment causes security and or other process issues. Further COVID may present issues or delays in projects. | Operations | Generally unacceptable | Not likely | High | Y- Reviewed and determined no longer to be a risk for 2021 | Condudted a full process lifecycle risk identification and determined low risk. Establish scalable processes and support mechanisms (Remote work, Infrastructure) Provided formal customer and employee communications at various stages in response.
External Market Conditions (Oil Prices) cause Churn in Customer Base | Sales | Tolerable | Possible | Low | Y- Proved that our mitigation has worked from 2020 Risk Assessment. | Expansion/Diversification into other verticals (i.e. Healthcare, Manufacturing, Aerospace) 2020 performance has included expansion at Lockheed and 2019/2020 new customer verticals such as Healthcare, Professional Services, Technology and Manufacturing
Higher exposure with corporate entities brings a higher threat of Cyber attack | Product Development | Generally unacceptable | Possible | High | Y- New Risk | Evaluate cyber Insurance policy coverage Additional resource focused on Product Engineering Deployed additional threat mitigation and monitoring across Infrastructure and business applications

## MGT Approval
Date of Review | Attendees | Summary
2024-05-30 | Jai Shah- CEO Tom White- VP Product Sadia Lin- VP Engineering Sean Rohde- VP Sales Aaron Roach- VP Customer Success Gail Plusquellec- Dir of People & Finance | Reviewed and Approved during Management meeting